## Sheet1
Priority | Seis Zone Task | Effort |  | Reason | Group
1 | QI Fix Remove TSM | 2 weeks | Dev | QI's are unreliable and slow and dependant upon system load, need direct access to data for QI's. | 1
2 | Fix MyFocus | 1 Week | Dev | Reduce dependancey on legend left hand, major improved in whole process. | 1
3 | Fix Cart/Process 2 weeks | 2 Week | Dev | Make it consistent with MyFocus | 1
4 | Fix History 2 weeks (Phase 1) | 2 Weeks | Dev | This will need to be review when Sale and Trade in rewritten. | 1
5 | Adjust Pricing | 1 week | Dev | Make provision for management fees. | 1
6 | Enhance Login | 4 weeks | Dev | Align for Eyeglass and non eyeglass users. Center map, layer peferences, extend security and BA requirements etc. | 1
7 | Implementation of FME | 2 Weeks | Dev | Add FME server to the architecture. | 2
8 | Change QI Packages | 4 Week | Dev | Service, download, resubmit, etc. | 2
9 | Partnerhip Approvals | 2 Weeks | Dev | Automated generation of partnership Approval | 2
10 | S&T Upgrade | 13 weeks | Dev | Need major extensions and upgrade !seiszone then client. | 3
11 | Fix Legend Layer Control | 4 weeks | Dev | Clean up the legend and make provision in database for other layer types | 4
12 | Define Region | 2 weeks | Dev | Canada, United States, Europe, Asia | 4
40 weeks